# Moyopay Prelaunch Campaign Plan

Window: 10 weeks (2–3 months), flexible to 8–12 depending on how fast the waitlist moves.

Starting point: 1.4k+ already on the waitlist

Target: 5,000 total waitlist signups → converted into a launch-day advocate base

## 1. Campaign Overview

Objective: Grow the Moyopay waitlist from 1.4k to 5k through a story-led content push (paired with a small, tightly-targeted Facebook/Instagram budget), then convert that list into activated advocates who create buzz ahead of launch.

Secondary objective: Build a warm, pre-sold cohort so launch day converts waitlist → active users at a high rate, instead of just having a big inert list.

Three phases:

| Phase | Weeks | Goal |
| --- | --- | --- |
| 1. Story Activation | 1–2 | Land the core narrative, seed it across owned channels, build creative assets |
| 2. Growth Sprint | 2–8 | Push from 1.4k → 5k via content + paid |
| 3. Advocate Conversion | Trigger: hitting 5k → through launch | 12-email sequence, turn waitlist into promoters, build launch-week buzz |

Phases 1 and 2 overlap deliberately — we don't wait for the story to "land" before we start running ads against it, you let the ads amplify whatever is already resonating organically.

## 2. The Activating Story Angle

Here's my proposed core narrative, built from what's actually true about Moyopay (dollar stablecoin wallet, no bank required, launching Nigeria first, non-custodial, licensed rails)

Core angle: "Your salary is losing a race you never signed up for."

The naira devalues. Savings in naira devalue with it. Everyone in the target audience already feels this, it's not a hypothetical pain point, it's a monthly gut-punch. Moyopay's counter-story isn't "here's a fintech app"; it's "stop losing to a currency you can opt out of."

Supporting narrative threads to rotate through content:

- The freelancer thread — get paid by a client abroad, keep it in dollars, no wire fees, no "rejected transfer" horror stories

- The saver thread — naira in a bank account depreciates while you sleep; dollars in Moyopay earn yield while you sleep

- The "no bank required" thread — for the underbanked/unbanked segment, a real dollar account from a phone, no paperwork

- The trust thread — non-custodial, CBN-licensed partners, Visa/Mastercard issued through regulated members (this is your answer to "is this just another crypto app that'll rug me")

Each piece of content in Phase 1–2 should trace back to one of these threads, always under the umbrella line. This is what "doubling down" means in practice: not a new angle every week, but new angles on the same wound.

## 3. Target Audience

Primary: Nigerian professionals and freelancers, 22–38, urban/semi-urban, earning in naira (or partly in USD as freelancers), painfully aware of currency depreciation, moderately online, active on Instagram/X/Telegram, has tried at least one crypto or fintech app before.

Secondary: Diaspora-adjacent Nigerians sending money home, and small business owners who invoice internationally.

Where they already are: Twitter/X fintech and crypto Nigeria conversations, Instagram, Telegram groups (crypto and hustle-economy communities), WhatsApp broadcast culture, and increasingly TikTok for financial literacy content.

Objection to pre-empt everywhere: "Is this safe / is this just crypto in a trench coat?" Trust and regulation messaging has to appear early and often, not just in the FAQ.

## 4. Channel Strategy

| Channel | Role | Effort |
| --- | --- | --- |
| X/Twitter (existing) | The primary growth engine — real-time commentary on naira/currency news, threads, viral moment engineering, reply-guy presence | High |
| LinkedIn | Founder-voice narrative posts, credibility/trust building with a more professional and diaspora-adjacent audience, positions Moyopay in fintech-founder conversation | Medium-High |
| Instagram (existing) | Storytelling feed — Reels for the story angle, carousels for trust/education | High |
| Telegram (existing) | Direct community, AMAs, early-access drip, waitlist-only content | Medium |
| Blog (moyopay.io/blog) | SEO-anchored trust content ("Is Moyopay licensed," "How stablecoin savings work") | Medium |
| Email (from 1.4k+ list) | Reactivate existing waitlist immediately — cheapest 3.6k you'll ever get partially comes from re-engaging people who already raised their hand | Low |
| Facebook/Instagram Ads | Small, optional supplement — not the growth mechanism | Low spend, low priority |

Growth is not dependent on paid spend. The 3.6k needed to hit 5k is expected to come primarily from organic virality on X and LinkedIn (Section 4b) plus the referral loop, not from the ad budget. The $30 is a side experiment, not load-bearing.

### On the $30 ad budget

$30 can't move the needle on its own in this market, and it isn't meant to. Keep it strictly secondary:

- Retargeting people who visited moyopay.io but didn't join the waitlist (warmest possible audience)

- Boosting the single best-performing organic post each week, capped small, to see what a slightly wider audience does with it

Treat it as a signal-gathering tool. If it teaches you something about which thread converts, good — but the plan does not fail if this budget does nothing.

## 4b. Organic Virality Playbook — X and LinkedIn

This is where the actual 3.6k growth is expected to come from. Virality isn't luck here — it's putting the same story angle through formats that are built to travel.

On X:

- Currency-news reactions. The moment naira news breaks (devaluation, CBN policy, exchange rate milestones), have a reaction thread ready within hours. Fast, sharp commentary on real news consistently outperforms scheduled content — this is your single highest-leverage tactic.

- "Receipts" format posts. Screenshot-style posts showing the actual cost of naira depreciation over a year, or a side-by-side of what $100 could buy vs. what ₦100k can now buy — visual, shareable, quote-tweet bait.

- Contrarian/bold-claim openers. Threads that open with a statement people want to argue with or co-sign publicly ("Your savings account is a slow leak, not a safety net") get replies and quote-tweets, which is what actually spreads a thread beyond followers.

- Reply-guy presence in fintech/crypto Nigeria X. Genuinely useful, sharp replies in the bigger accounts' threads (not spam) puts the brand in front of audiences you didn't pay to reach.

- Founder-voice threads, not brand-voice. A named person telling the "why we're building this" story consistently outperforms a logo account saying the same thing.

On LinkedIn:

- Founder narrative posts. LinkedIn rewards a personal, reflective voice — "why I started building a dollar wallet for Africa" performs very differently there than on X. Same angle, more vulnerable/considered tone.

- Data-led posts. A short, well-designed post breaking down the stablecoin volume numbers already on the Moyopay site ($54B+ annual volume, 200M+ unbanked adults) positions the founder as someone who understands the market, which pulls in press, investors, and diaspora professionals — a different but valuable audience for word-of-mouth.

- Milestone posts. "We just crossed 3,000 on the waitlist" style posts, timed to the countdown in the content calendar, work well on LinkedIn specifically because the platform's culture already rewards public progress updates.

Cadence: X needs near-daily presence (reactive + planned) to have a shot at virality — it rewards frequency. LinkedIn works on a lighter, 2–3x/week cadence of higher-effort posts; more isn't better there.

What "viral" actually looks like for this budget-free plan: not one post everyone assumes will blow up, but a high volume of well-targeted attempts across weeks 1–8, so that the story angle gets multiple real shots at catching. Track which thread (freelancer/saver/trust/no-bank) gets the most organic pickup each week and lean into it the following week — this is the actual replacement for what a paid budget would normally buy you: fast signal on what resonates.

## 5. Content Calendar (10-week view)

Weeks are thematic batches, not rigid daily slots — leave room to react to naira news or trending fintech conversations, which is often your best organic fuel.

| Week | Theme / Content Focus | Channel | Notes |
| --- | --- | --- | --- |
| 1 | Launch the "losing race" angle — 1 hero Reel/video, 1 founder-voice X thread, 1 blog post on naira depreciation data | IG, X, Blog | Sets the narrative umbrella everything else sits under |
| 2 | Freelancer thread — testimonial-style story content ("what if you never had a wire transfer rejected again") | IG, X | Start light retargeting ads on site visitors |
| 3 | Trust thread — "is Moyopay licensed" explainer, CBN/Visa/non-custodial breakdown | Blog, IG carousel | Pre-empt the #1 objection before it's asked at scale |
| 4 | Saver thread — dollar yield vs naira savings account comparison, simple visual | IG, X | Boost this post if it performs |
| 5 | Reactivate existing 1.4k — dedicated email to current waitlist: referral push + sneak peek content | Email, Telegram | Cheapest growth lever available |
| 6 | UGC seeding — invite early waitlisters to share why they joined, repost their voices | IG, X | Starts the advocate flywheel before you even hit 5k |
| 7 | Freelancer + saver thread remix using any UGC/testimonials gathered | IG, X | Content gets easier once real voices exist |
| 8 | Momentum push — countdown-style content as you approach 5k, social proof ("X joined this week") | IG, X, Telegram | Retarget hard here; this is the sprint |
| 9 | Trigger: hit 5k. Announce publicly, kick off 12-email sequence (Section 6), begin advocate program | Email, IG, X | See Section 7 for advocate mechanics |
| 10 | Buzz-building to launch — behind-the-scenes, countdown, advocate spotlights, launch-week teaser | All channels | Sets up whatever your actual launch week plan is |

Content pieces needed, in priority order:

- Hero "losing race" video/Reel — must-have, everything else references it

- Trust/licensing explainer (blog + carousel) — must-have, kills the #1 objection

- Reactivation email to the 1.4k — must-have, fastest path to momentum

- UGC/testimonial prompt for existing waitlisters — must-have for Phase 3 advocate base

- Retargeting ad creative (2–3 variants of the hero angle, cut for FB/IG) — must-have for the $30 to do anything

- Countdown/milestone social template — nice-to-have, reusable each time you hit a number

## 6. The 12-Email Sequence (triggers at 5k)

This isn't a generic nurture sequence — it's built to do two things at once: educate/build trust before launch, and convert the list into people who'll actually post, refer, and show up on day one. Structure below; I can draft full copy for each once you confirm the arc works.

Narrative arc: You made it onto something real (belonging) → here's why it matters for you specifically (education) → here's proof it's not a scam (trust) → you get to help build this (advocacy) → launch is close, don't miss it (urgency).

| # | Subject Line Direction | Purpose | Timing | Primary CTA |
| --- | --- | --- | --- | --- |
| 1 | "You're one of 5,000. Here's what that means." | Welcome + confirm they're part of something with momentum | Day 0 | Follow on IG/X for daily countdown |
| 2 | The naira story, told straight | Reinforce the core angle with data, not just feeling | Day 3 | Read the full blog explainer |
| 3 | "Is this safe?" — answered in full | Trust: licensing, non-custodial, Visa/Mastercard | Day 6 | Share with a friend who's skeptical |
| 4 | Freelancer-focused spotlight | Segment-relevant proof for the freelancer thread | Day 9 | Reply with your biggest cross-border payment headache |
| 5 | Saver-focused spotlight | Segment-relevant proof for the saver thread | Day 12 | Calculate what naira depreciation has cost you |
| 6 | Meet the team / why we're building this | Humanize the brand, deepen trust further | Day 15 | Reply to an AMA prompt |
| 7 | Referral program launch | Turn passive waitlisters into active recruiters | Day 18 | Share your unique referral link |
| 8 | Early access tiers / Pioneer perks explained | Reward the ones who move first | Day 21 | Check your position on the list |
| 9 | UGC roundup — real voices from the waitlist | Social proof from peers, not the brand | Day 25 | Submit your own "why I joined" |
| 10 | Launch date announced | The big one — concrete date, what happens next | Day 30 | Add to calendar / set reminder |
| 11 | Countdown — what to expect on day one | Reduce launch-day friction, set expectations | Day 35 | Prepare — link to a "getting started" guide |
| 12 | We're live | The payoff | Launch day | Download / open your account |

Exit condition: Anyone who opens the app or completes signup during the sequence exits immediately into a separate onboarding flow — don't keep selling to someone who already converted.

Branching note: If someone clicks the referral link in email 7 but doesn't complete a referral by email 9, send a lighter nudge instead of piling on more asks.

## 7. Converting Waitlist Into Advocates (Phase 3 core mechanic)

This is the piece most prelaunch campaigns skip, and it's the one you specifically asked for — so it deserves its own structure, not just "email 7 has a referral link."

- Give them a name, not just a spot on a list. Moyopay already has "Pioneer" branding from the closed program — resurrect it. "Pioneer" status for the first 5k gives people an identity to perform, not just a place in a queue.

- Referral loop with visible progress. A simple leaderboard or milestone unlock ("refer 3 friends, unlock X") does more work than a generic "invite your friends" line — it's visible, and Nigerians respond well to leaderboard/rank dynamics.

- UGC prompts tied to the story angle, not generic testimonials. Ask "what's the naira cost you this year?" not "why did you join Moyopay?" — the first gets an emotional, shareable answer; the second gets a polite one nobody reposts.

- Spotlight real people publicly. Reposting a waitlister's answer with their handle tagged turns one quiet signup into a small public moment they'll want to share themselves.

- Give advocates something to do on launch day specifically — a coordinated "go live" moment (post a specific graphic, use a specific hashtag) so launch morning looks and feels like a wave, not a scatter of individual posts days apart.

## 8. Success Metrics

| Metric | Target | Tracked via |
| --- | --- | --- |
| Waitlist growth (1.4k → 5k) | +3.6k over ~8 weeks | Site analytics / waitlist tool |
| Cost per signup (paid) | Track from day 1 of retargeting | Meta Ads Manager |
| Email open rate (12-email sequence) | 30-45% (lead-nurture/launch benchmark) | Email platform |
| Referral-driven signups | Track % of total from referral links | UTM/referral tracking |
| UGC submissions | Directional — quality over volume | Manual tracking |
| Launch-day activation rate | % of 5k who open the app in week 1 | Product analytics |

Reporting cadence: Weekly waitlist-count check-in during Phase 2 (this is your main lever to know if content or ads need adjusting); full review at the 5k trigger point before the email sequence goes live.

## 9. Risks and Mitigations

- Risk: Organic virality is inherently unpredictable — X/LinkedIn moments can't be guaranteed on a schedule. Mitigation: high volume of well-targeted attempts (Section 4b) across 8 weeks rather than betting on one post, plus the referral loop and reactivation email as non-viral-dependent growth levers running in parallel.

- Risk: One story angle fatigues the audience before 5k is hit. Mitigation: the four narrative threads (freelancer, saver, no-bank-required, trust) give you rotation inside the same umbrella angle — same wound, different angle of entry.

- Risk: Waitlist grows but doesn't convert to activated users at launch. Mitigation: the advocate mechanics in Section 7 exist specifically to keep the list warm, not just large.